## Sheet1
Sr No. | Task name | Description | Status | Start Date | End Date
1 | Download and load dataset | 1- Download the dataset from kaggle link -https://www.kaggle.com/datasets/vivek468/superstore-dataset-final 2 - Load the data set to the S3 bucket my-bucket71 | Complete | 22-03-2022 | 22-03-2022
2 | Create database | Create a database SF_Project_1 | Complete | 22-03-2022 | 22-03-2022
3 | Create schema | Create a schema ITR_RDS-1 / ITR_Landing_1 | Complete | 22-03-2022 | 22-03-2022
4 | Create a datamart schema | Create a datamart schema - ITR_DIS_1 | Complete | 22-03-2022 | 22-03-2022
5 | Create a table | Create a table SUPERSTORE as per the data set | Complete | 22-03-2022 | 22-03-2022
6 | Create an external stage | Create external stage SUPERSTORE_STAGE for loading the data structure | Complete | 22-03-2022 | 22-03-2022
7 | Create a snowpipe | Create Snowpipe SUPERSTORE_PIPE for auto ingesting data from S3 bucket my-bucket71 | Complete | 22-03-2022 | 22-03-2022
8 | Create a stream | Create stream SUPERSTORE_STREAM on table SUPERSTORE | Complete | 23-03-2022 | 23-03-2022
9 | Create SCD | Perform SCD 2 operation on consumer table SUPERSTORE_TARGET as per changes happen in the source table SUPERSTORE | Complete | 23-03-2022 | 24-03-2022
10 | Create a task | Automate data load from snowpipe to consumer table SUPERSTORE_TARGET on everyday at 12 pm | Complete | 23-03-2022 | 23-03-2022
11 | Data Analysis | Perform the below analysis on the data set 1. Calculate the number of Orders those with Ship Mode as ‘Second Class’ 2. List down the most valuable customers Country wise 3. Total Sales for Category ‘Furniture’ 4. Which Product provides the maximum profit 5. Calculate the total profit made by each product category country wise 6. Which region of United States have majority loss? | Complete | 24-03-2022 | 24-03-2022